DERBYSHIRE COUNTY COUNCIL

Agenda Item 5

Rep 615

SCHOOLS FORUM

18th February 2015

Report of the Acting Strategic Director

for Children & Younger Adults

Derbyshire’s Early Help Offer – Progress Report

- Purpose of the report

This report seeks to:

- Update the Schools Forum on the decision made by the Secretary of State regarding Derbyshire’s Early Help offer;

- Set out roles and responsibilities for this project and the reporting protocol; and

- Update the Schools Forum on the project and agree the consultants’ project plan.

- Information and Analysis

The Authority has now been informed that the Secretary of State for Education has decided to approve Derbyshire’s application to retain funding within the central Schools Block for 2015-16. Specifically, the approval allows the Authority to use £1m of the £16.2m increase in Schools Block DSG for 2015-16, together with £2m from retained centrally held DSG underspends, to support the early help joint commissioning arrangements with schools.

The proposed roles and responsibilities for this project are:-

Project Board – Schools Forum

  - Authorise each stage of the project.

  - Provide overall guidance and direction to the project, ensuring it remains viable.

  - Ensure that risks are being tracked and managed as effectively as possible.

  - Approve scope and changes to be included in any Cabinet reports.

Project Sponsor - (Assistant Director – Schools and Learning)

  - Monitor and control the progress of the project at a strategic level.

  - Make decisions on issues escalated by the Project Manager.

  - Ensure that this project is on target to deliver the savings target within the agreed time scales.

Key Practitioners – (Service Director – Safeguarding and Disability) & (Acting Assistant Director – Universal and Targeted Services)

  - Ensure all relevant early help services are considered to be included within the scope of this project.

  - Advise on the effects on the service schools will receive as any changes are made.

  - Advise on the level of service which continues to be provided by the Local Authority and the additional/enhancing services that may be funded by the monies pooled by the schools.

Project Manager – (Programme Officer)

  - Day to day running of the project.

  - First point of contact for the consultants.

  - Maintain relevant reports including a risk register.

  - Report any issues to the project sponsor.

  - Manage information flows between the Project Board, Project Sponsor, Project Consultants and Stakeholders.

  - Assist in the facilitation of any meetings needed.

Facilitators Group – attached list Appendix 1

  - Participate in stakeholder meetings to ascertain views on any proposals.

  - Feedback relevant information to colleagues.

Key Practitioner – (Senior Programme Manager)

  - Advise on project management issues.

  - Ensure Support and Aspiration issues are considered.

Key Practitioner – (Head of Finance)

  - Advise on financial issues.

Consultants -

  - Engage with stakeholders across the 413 schools and academies in Derbyshire, and from across the Children’s Trust Partnership, in the co-design and production of new arrangements.

  - Develop a robust and sustainable business case for the new commissioning arrangements and joint investment board.

  - Assist in the development of new governance and operational arrangements to achieve the identified benefits of delivering excellent, cost effective and sustainable early help.

  - Produce a business model which will be financially sustainable and an operating model on how the service might be organised.

It is suggested that the Early Help offer should be a standing item on each Schools Forum agenda as well as monthly updates being provided to the Children and Younger Adults’ Senior Management Team and Elected Members.

The consultants have started to perform background research with both Schools and MAT teams. The first Facilitators group workshop is due to take place on 3rd February. The consultants have produced a proposed Project Plan (Appendix 2).

- Financial Considerations

The Strategic Director for Children and Younger Adults has already approved the appointment of facilitators to produce a proposal for initial review at a maximum cost of £20,000.   If this model is agreed to be viable, then the next stage would be to run and evaluate a pilot of the model between April 2015 and August 2015.  The maximum expected cost of this stage is expected to be £30,000.

Should the pilot be successful, further scaling would then take place to expand the model throughout all the schools in Derbyshire.  The timetable for this stage is provisionally set for September 2015 to August 2016 and the anticipated cost is a further £30,000.

The total potential cost for these three stages would be £80,000 which will be funded from CAYA’s own resources.

- Acting Strategic Director’s Recommendations

That the Schools Forum agree:

- To act as the Project Board for this major development;

- To the other proposed roles and responsibilities as set out in section 2; and

- The proposed Project Plan in Appendix 2.

IAN JOHNSON

Acting Strategic Director for Children & Younger Adults

Wicked Issue – Facilitators Group 	Appendix 1

Project Plan	Appendix 2