DERBYSHIRE COUNTY COUNCIL

Rep 643

Agenda Item 4

SCHOOLS FORUM

9 November 2015

Report of the Strategic Director for Children’s Services

Progress – Radical Rethink of the Early Help Offer Cluster Prototypes

- Purpose of the report

This report seeks to update the Schools Forum on the progress of the radical Rethink of the Early Help Offer Cluster Prototypes and share the learning to help inform a co-commissioned model.

- Information and Analysis

  - Context

2.1.1 	In December 2014 the Schools Forum approved:

- The development of four prototypes across Derbyshire to test out new models of joint working between schools and Early Help Services (Multi-Agency Teams).

2.1.2		The four prototypes are:

- Whittington Green Cluster – Chesterfield

- Kirk Hallam Cluster – Erewash

- Hope Valley Cluster – High Peak

- Heanor Gate Cluster – Amber Valley

2.1.3	The work on the prototypes started in February 2015 and in July 2015 three further secondary schools in South Derbyshire requested permission to be included in the prototypes.  This was approved by the Schools Forum.

  - Progress of the Prototypes

2.2.1	Whittington Green Cluster

The work on this prototype started in April 2015 and it is led by the secondary school headteacher and Multi-Agency Team manager.

Re-design and improvements include:-

- Joint Governance meetings – secondary, primary and Multi-Agency Teams (MATs) to improve communication, planning and re-designing services.  Health and voluntary sector colleagues are also invited.

- Pooling of school pastoral support resources to deliver an improved home visiting service so that all families are supported to ensure their children are school ready.

- Agreeing to have one school attendance policy across the cluster so parents receive consistent information and to improve attendance and reduce persistent absence.

- Improving transition arrangements in Year 6 and Year 7 across the cluster.

2.2.2	Kirk Hallam Cluster

The work on this prototype started in April 2015 and is led by the secondary school headteacher and the Multi-Agency Team manager.  The Multi-Agency Team has been co-located with the school since April 2011 and the prototype has provided an opportunity to strengthen the already good joint working arrangements on site.  Re-design and improvements include:-

- Strengthened governance with fortnightly meetings established including Police and Health to improve the joint working and to allocate Starting Point referrals/requests.

- Re-focus the cluster boundary to deliver Early Help services to families based on the school their children attend rather than where they live.

- To improve communication and information sharing through increased access to case recording systems (Frameworki).

- To improve school readiness with primary schools increasing their involvement in Children’s Centre Advisory Groups.

2.2.3	Hope Valley Cluster

The work on this prototype started in June 2015 and is led by the Chair of Governors, the secondary school headteacher and the Multi-Agency Team manager.  There is accommodation on the Secondary School site for a co-located Multi-Agency Team.  Re-design and improvements include:-

Improved joint working with the Multi-Agency Team which is now co-located on the school site.

- Joint governance meetings have been established to improve the responsiveness and effectiveness of Early Help Services.

- Three pastoral lead roles have been established in the Secondary School and the cluster is exploring options to appoint a Primary School pastoral lead to improve transition and joint working between the schools.

- A priority for the cluster is to improve school readiness and improve access to services for families living in rural areas.

2.2.4	South Derbyshire Cluster

The work on this prototype started in July 2015 and is led by the secondary school headteachers and the Multi-Agency Team manager.  The prototype decided to include three secondary schools in the Swadlincote area as there are existing strong joint working arrangements between the schools and strong partnership working.  Re-design and improvements include:-

- Establishing joint governance arrangements to improve communication, re-design of services and the responsiveness and effectiveness of Early Help Services.

- Explore options for the pooling of resources to improve school readiness.  Health, the voluntary sector and the district council are involved in the cluster.

- Explore joint commissioning in the primary schools of counselling services to deliver a more cost effective service.

- Improving attendance and reducing persistent absence is a priority for the cluster.

2.2.5	Heanor Gate Cluster

The work on this prototype started in September 2015 and is led by the primary school headteachers and the Multi-Agency Team manager.  The school cluster has existing strong joint working arrangements and its priority is to improve joint working with the Multi-Agency Teams.

Re-design and improvements include:

- Explore the boundary with the school cluster and the Multi-Agency Team as the cluster currently covers two Multi-Agency Teams in the Amber Valley locality and one Multi-Agency Team in Erewash locality.

- Improve school readiness by schools increasing their involvement in Children’s Centres, health services and with childcare providers.

- Establish governance meetings to strengthen multi-agency decision- making of Starting Point referrals across the cluster and MAT.

3.	Learning from the Cluster Prototypes to inform the Co-commissioned Model

Key themes from the cluster prototypes are:-

- A commitment from all schools involved to maintain Early Help Services through joint investment between schools and Multi-Agency Teams.

- Governance arrangements have been established to explore opportunities to make further efficiencies and also to explore service re-design and service improvement.

- Improved joint operational delivery e.g. fortnightly multi-agency meetings involving partners and establishing a named school/MAT link worker for all schools.

- Undertaking needs assessments by mapping available resources and identifying duplication and gaps to inform service re-design and service improvement.

- Identifying pooled budgets across schools to deliver service improvements e.g. outreach family support service.

- Exploring re-commissioning opportunities e.g. counselling services provided by the voluntary sector in Primary schools – ensuring efficiencies and service improvement.

- Improving communication to families e.g. Early Help Services are included on schools websites and agreeing a joint Attendance Policy.

- Improved information sharing – improved access to case recording systems (Frameworki).

- Improved use of staff resources across schools and Multi-Agency Teams to prevent duplication, e.g. lead worker across the cluster to work with a family rather than several staff visiting the home.

- Shared ownership of the school cluster and MAT boundaries which is improving communication with neighbouring Multi-Agency Teams and local authorities.

- A commitment to improve school readiness e.g. increasing primary school involvement in integrated service delivery with Children’s Centres, including Health.

- Exploring joint working with the voluntary sector to improve universal services to reduce referrals to Early Help and specialist services and explore opportunities for income generation.

4.	Strategic Director’s Recommendations

Schools Forum is asked to note the progress to date within the cluster prototypes and the learning that will inform a co-commissioned model.

IAN JOHNSON

Strategic Director for Children’s Services