Agenda Item No 5

Rep 656

DERBYSHIRE COUNTY COUNCIL

SCHOOLS FORUM

11 February 2016

Joint Report of the Strategic Director for Children’s Services

and Director of Finance

DEDICATED SCHOOLS GRANT (DSG) SPENDING 2015/16

- Purpose of the report

To inform Schools Forum of the results of the latest DSG budget monitoring and to highlight major variances.

2. 	Information and Analysis

2.1 	General

This report provides an analysis of the latest forecast year end position for expenditure funded by the Dedicated Schools Grant (DSG) 2015-16 based on income and expenditure up to the end of December.

A breakdown of the spend against budget by service is attached as Appendix 1.

2.2	Dedicated Schools Grant (DSG)

The Authority retains control over spending on children and young people with additional educational needs in schools (including academies and independent/non maintained sector as well as maintained schools) and the specialist support services that work with those pupils.

The expenditure against the Dedicated Schools Grant is projected to be £456,012k against a grant of £459,216k, an underspend of £3,204k.

The main areas of underspend are:

Additional funding received in relation to 2014/15			£322k

Early Years expenditure

The Early Years block of the DSG for 2014/15 is only finalised during July 2015 when a final adjustment is made to reflect the pupil numbers on the January 2015 Early Years census.  As the January 2015 census was higher than the January 2014 census, an additional payment of £322k was received.  Payments to PVI settings, nursery schools and primary schools with nursery classes were made in 2014/15 based on the pupils recorded on the January 2015 census so this is additional funding received towards costs that had already been incurred in the 2014/15 financial year.

Allocation for Unifi								£500k

When setting the spending plans for 2015/16, Schools Forum agreed to support proposals to introduce an endowment fund for children in care.  As explained at a previous meeting of Forum, the Authority’s plans have now changed and therefore this contribution from the DSG is no longer required for that purpose.

Primary Key Stage 1 class size funding					£674k

Last year Schools Forum agreed a change in the qualifying criteria for support to schools requiring additional KS1 teachers to comply with the maximum class size regulations.  This has resulted in less expenditure against the budget which, in line with Forum’s wishes, was not reduced for 2015/16.

Re-pooled budgets (primary and secondary 				£350k

maintained schools)

The underspend is mainly on the contingency fund.  Underspends across the pooled budgets are ring-fenced and can only be used to contribute to re-pooled expenditure in future years or returned to maintained schools.

Early Years Private, Voluntary and Independent places	       £1,498k

The number of 3 and 4 year olds taking up places at PVI settings is projected to be lower than that assumed in the budget.  Allowing for the increase in rate per hour from £3.79 to £3.92, expenditure is 7.8% (£1,008k) higher than in 2014-15 due to an increase in the number of hours being paid for.  As explained earlier, the DSG will be adjusted in July 2016 based on the Early Years census count in January 2016 and any reduction to the number of children compared to January 2015 will mean that DSG is clawed back in 2016/17.  At this stage, it is felt prudent to assume that up to £500k could be clawed back.

Unallocated DSG									£376k

This underspend is as a result of changes to recoupment by the EFA since the original budget allocations for Schools Block, High Needs Block and Early Years Block were agreed last year.  The changes are due to a lower recoupment by the EFA for High Needs Block places for pre 16 children in non-maintained institutions and academies and post 16 young people in all institutions and adjustments in respect of recoupment for schools converting to academies during the year.

When a school converts part way through the year, up to 80% of the pro-rata DSG allocation for rates for that school is released due to the change in status of the school and the fact that an academy is automatically entitled to 80% rate relief.  If a school was a VA school prior to conversion to academy status, there is no release of the DSG allocation since the school was already benefitting from this relief.

These underspends are offset by the following projected overspends:

Secondary School High Needs top-ups					£148k

The projection for high needs top-ups is estimated to be £148k (2.4%) higher than the budget allocated.

Top-ups for young people in non-maintained and other 		£386k

local authority special schools

The projection for top-ups is estimated to be £386k (6.4%) higher than the budget allocated and is due more to a change in the mix of placements than an increase in the number of placements.

Provision of up to 15 hours placements for 2 year olds		£398k

The estimated cost of placements for qualifying two year olds is currently projected to be greater than the current allocation of grant to the Authority.  The final allocation will not be confirmed until July 2016 as it is dependent on the January 2016 census.  The DfE have prohibited any anticipation of increased income by local authorities and so the 2015/16 outturn will be adversely affected by any overspend in this area with the 2016/17 financial year benefiting from any subsequent increase to the grant paid.

2.2	Accumulated Dedicated Schools Grant funds

At the start of 2015/16, the balance of the DSG and other DSG originated earmarked reserves was £28,645k of which £25,031k was DSG brought forward.  During 2015/16, £14,655k has been used to support schools’ budgets as well as providing additional funding for Single Status costs, a contribution to the Early Help offer in Derbyshire, allocations for secondary school performance improvement, piloting different approaches towards Alternative Provision in clusters, the costs of Equal Pay and a contribution towards the capital costs of accommodating children with additional needs within Derbyshire schools.  Adjusting for the anticipated underspend of £3,204k in year and showing the element relating to de-delegated and re-pooled funds separately, the projected balance at the end of 2015/16 including DSG originated earmarked reserves is £13.580m, the table below provides a breakdown of this figure.

Table 1 - Dedicated Schools Grant projected reserves at 31st March 2016

|  | Opening Balance £m | Increase / (Decrease) £m | Closing Balance £m |
| --- | --- | --- | --- |
| Capital maintenance | 1.051 | (1.051) | 0 |
| 2 year old places – capital projects | 2.563 | (2.563) | 0 |
| De-delegated funds (DSG) | 1.253 | 0.350 | 1.603 |
| Dedicated Schools Grant – excluding de-delegated funds | 23.778 | (11.801)* | 11.977 |
| Total | 28.645 | (15.065) | 13.580 |

*Anticipated underspend in year less £14,655k support to the DSG in 2015/16 described above

  - Dedicated Schools Grant (DSG) commitments

The Schools Forum has previously agreed several allocations which will significantly reduce the amount of DSG cash reserves in the coming years. The latest position is set out below:

Table 2 – Potential/actual DSG commitments

| Item | Total |
| --- | --- |
|  | £m |
| Support for schools’ budgets (2016-17 to 2017-18) – estimate | 2.195 |
| Support for schools’ budgets (2018-19 to 2020-21) – estimate | 0.728 |
| Support for secondary schools (2016-17) | 3.500 |
| Agreed transitional support for QEGS | 0.061 |
| Rethink of Early Help Offer (REHO) (2016-17) | 2.000 |
| Transitional support for new schools | 3.000 |
| Potential clawback of Early Years underspend 2015/16 | 0.500 |
| TOTAL | 11.984 |

The total of potential commitments in future years estimated at £11.984m compares to the DSG excluding de-delegated funds estimated at £11.977m

3.	Background Papers

Files held in Children’s Services Finance - Accountancy section.

4.	Officers’ Recommendation

4.1	That Schools Forum notes the report.

IAN JOHNSON

Strategic Director - (Children’s Services)

PETER HANDFORD

(Director of Finance)

Appendix 1

Children’s Services - Financial Monitoring (spend to 31/12/2015)

Dedicated Schools Grant

|  | Full year budget 2015/16 £000s | Forecast year end actual 2015/16 £000s | Forecast year end (Under)/Over 2015/16 £000s |
| --- | --- | --- | --- |
| Central expenditure | 16,010 | 14,506 | (1,504) |
| Early Years | 22,646 | 21,344 | (1,302) |
| High Needs Block – Places & Top-ups | 37,679 | 38,322 | 643 |
| High Needs Block – other | 18,356 | 18,013 | (343) |
| Maintained School ISB | 363,827 | 363,827 | 0 |
| Grant Income | (458,518) | (459,216) | (698) |
|  | 0 | (3,204) | (3,204) |
| Less pooled budget underspend |  |  | (350) |
| Uncommitted DSG underspend [Note: Although uncommitted, a clawback could be made in 2016/17 relating to the 2015/16 Early Years Block allocation] |  |  | (2,854) |