DERBYSHIRE COUNTY COUNCIL

Rep 659

Agenda Item 4

SCHOOLS FORUM

11 February 2016

Report of the Strategic Director for Children’s Services

PROGRESS – RADICAL RE-THINK OF THE EARLY HELP OFFER (REHO)

- Purpose of the Report

This report seeks to update the Schools Forum on the progress of the Radical Re-think of the Early Help Offer (REHO).

- Information and Analysis

2.1	Context

The Radical Re-think of the Early Help Offer was initially driven by unprecedented cuts to Children’s Services which have reduced from £126 million in 2010/11 to £88 million in 2016/17.  Despite these cuts, schools, academies and the Local Authority are working together to develop new arrangements for providing essential Early Help services.

Since March 2015, schools, academies and Children’s Services Multi-Agency Teams have been working together in five prototypes across the County to develop a jointly invested Early Help service.  The Schools’ Forum agreed to a contribution of the DSG to be retained centrally by the Local Authority, for 2016-17 however, this request was refused by the Secretary of State for Education.  Therefore, the Authority was required to delegate the DSG to individual schools and academies with a request to schools and academies to re-pool.  As a result of this, it is proposed that a jointly invested Early Help Service, and the learning from the prototypes, will be rolled out County-wide from April 2016.

2.2	Proposal for County-wide Implementation of REHO

The proposed timeline is as follows:

| Early January | Letter to individual schools in Derbyshire outlining the proposals for implementation of REHO. |
| --- | --- |
| Mid-January | Letter to individual schools to inform them of their indicative budget for 2016-17. |
| February | REHO locality events with an invitation to all school clusters and Early Help Services led by the prototype leads. These events will provide more detail on the Early Help Offer and the proposals for the Locality Commissioning Hubs. |
| Early March | Letter to individual schools asking for their decision on the request to re-pool the DSG funding for the joint investment and re-design of Early Help Services. |
| February/ March | School Governors will be briefed on the proposals for rolling out a jointly invested Early Help Offer to all school clusters by April 2016. |
| March | A report on the proposals for a jointly invested Early Help Service and approval to implement the proposals will go to Derbyshire County Council’s Cabinet. |
| September | Subject to Cabinet approval, and with agreement from schools to re-pool the DSG funding, it is proposed that the Locality Commissioning Hubs will be implemented. |

2.3	Multi-Agency Team Lead Contacts

MAT Manager lead contacts in each locality:

- High Peak/North Dales	Faye Edwards	(01629) 533848

- Chesterfield			Helen Smythe	(01629) 533557

- North East/Bolsover		Brenda Towse	(01629) 537173

- Erewash			Doug Neely		(01629) 532666

- Amber Valley			Marie Eastwood	(01773) 767982/(01629) 530892

- South Derbyshire		Ian Stevens	(01283) 229709

2.4	Radical Re-think of the Early Help Offer – Locality Events

See Appendix 1.

2.5	Radical Re-think of the Early Help Offer – Locality Commissioning Hubs

Proposals for Locality Commissioning Hubs are in the early stages of development and more detailed work is planned from January 2016 by the REHO Governance Group.

It is proposed that there will be Locality Commissioning Hubs in each of the six localities in Derbyshire.

Representatives will include:

- School clusters

- Heads of Service Locality – Derbyshire Children’s Services

- Public Health

- Commissioning Manager

- Other partners based on locality/community needs

The Locality Commissioning Hubs will have the responsibility of commissioning and re-designing Early Help Services locally.  In order to do this, the Hubs will be supported with information on the commissioning process, including:

- Needs Assessment

- Budgets and arrangements for pooling budgets

- Financial monitoring

- Performance data

- Governance and reporting responsibilities

For schools which do re-pool, there is a great opportunity to redesign Early Help Services and improve outcomes for children.  The opportunities include:

- co-location

- Improved school readiness

- Improved attendance

- Improved transition arrangements

and full development of a Team Around the School model which will improve attainment and Ofsted judgements.

More detailed information on the plans for Locality Commissioning Hubs will be discussed at the REHO Locality Events.

- Strategic Director’s Recommendation

Schools Forum notes the progress of the proposals to implement the Radical Re-think of the Early Help Offer county-wide.

IAN JOHNSON

Strategic Director for Children’s Services

APPENDIX 1

| District | Date | Time | Venue |
| --- | --- | --- | --- |
| Erewash | 3 Mar | 11.00 am – 1.00 pm | Kirk Hallam Community Academy, Godfrey Drive, Ilkeston, Derbyshire, DE7 4HH |
|  | 25 Feb | 12.30 pm – 2.30 pm | Wilsthorpe Community School, Derby Road, Long Eaton, Derbyshire, NG10 4WT |
| North East & Bolsover | 24 Feb | 2.30 pm – 4.30 pm | Gladys Buxton Adult Education Centre, Oakhill Road, Dronfield, S18 2EJ |
|  | 26 Feb | 1.30 pm – 3.30 pm | Clay Cross Adult Education Centre, Market Street, Clay Cross, Chesterfield, S45 9JE |
| Chesterfield | 23 Feb | 2.00 pm – 4.00 pm | Donut Creative Arts Studio, Spring Bank Rd, Chesterfield, S40 1NL |
|  | 24 Feb | 10.00 am – 12 noon | Peter Webster Centre, Sheffield Road, Chesterfield, S41 8LQ |
| High Peak | 2 Mar | 10.00 am – 12 noon | Fairfield Adult Education Centre, St Nicolas Hall, Victoria Park Road, Fairfield, Buxton, SK17 7PE |
|  | 2 Mar | 1.00 pm – 3.00 pm | Fairfield Adult Education Centre, St Nicolas Hall, Victoria Park Road, Fairfield, Buxton, SK17 7PE |
| Amber Valley | 23 Feb | 9.30am – 11.30am | Howitt Primary Community School, Holmes Street, Heanor , Derbyshire, DE75 7FS |
|  | 23 Feb | 1.30pm – 3.30pm | Howitt Primary Community School, Holmes Street, Heanor , Derbyshire, DE75 7FS |
| South Derbyshire | 2 Mar | 2.00pm – 4.00pm | John Port School, Exam Centre Block (EC3), Main Street, Etwall, Derbyshire, DE65 6LU |
|  | 3 Mar | 10.00 am – 12 noon | Adult Education Centre, Rink Drive, Swadlincote, DE11 8JL |