DERBYSHIRE COUNTY COUNCIL

Rep 651

Agenda Item 4

SCHOOLS FORUM

16th December 2015

Report of the Strategic Director for Children’s Services

PROGRESS – RADICAL RETHINK OF THE EARLY HELP OFFER (REHO)

- Purpose of the report

This report seeks to update the Schools Forum on the progress of the Radical Rethink of the Early Help Offer (REHO) and seeks approval for the implementation of REHO county-wide.

- Information and Analysis

  - Context

The five prototypes:

Whittington Green Cluster – Chesterfield

Kirk Hallam Cluster – Erewash

Hope Valley Cluster – High Peak

Heanor Gate Cluster – Amber Valley

South Derbyshire Cluster – Swadlincote

These continue to make progress to develop and implement a jointly invested, redesigned Early Help Offer.  In order to ensure there are prototypes in all localities in Derbyshire, there is a meeting to discuss the North-East and Bolsover schools in December.

Following the Secretary of State’s decision not to approve Derbyshire’s request to centrally retain £5m of Dedicated Schools Grant (DSG), it is proposed that the DSG will be largely delegated to individual schools from April 2016 (for Academies this will be September 2016).  The detail of this is covered in the report: DSG funding 2016-17.  Between now and April 2016, the priority for REHO is to ensure the prototype work continues and that this work is rolled out to all school clusters in Derbyshire from April 2016.

Between now and April 2016, the priority for REHO is to ensure the prototype work continues and that this work is rolled out to all school clusters in Derbyshire from April 2016.

  - Proposal for County-wide Implementation of REHO

The proposed timeline is as follows:

| Early January | Letter to individual schools in Derbyshire outlining: - REHO prototype work to date - Details of the Early Help Offer in each locality and an outline of the consequences of not re-pooling for joint investment of Early Help Services - Proposals for Locality Commissioning Hubs - Details of Locality Events planned for February |
| --- | --- |
| Mid-January | Letter to individual schools to inform them of their indicative budget for 2016-17. |
| February | REHO locality events with an invitation to all school clusters and Early Help services led by the prototype leads. These events will provide more detail on the Early Help Offer and the proposals for the Locality Commissioning Hubs. |
| Early March | Letter to individual schools asking for their decision on the request to re-pool the DSG funding for the joint investment and re-design of Early Help Services. |
| February/ March | School Governors will be briefed on the proposals for rolling out a jointly invested Early Help Offer to all school clusters by April 2016. |
| March | A report on the proposals for a jointly invested Early Help Service and approval to implement the proposals will go to the Council’s Cabinet. |
| September | Subject to Cabinet approval, and with agreement from individual schools to re-pool the DSG funding, it is proposed that the Locality Commissioning Hubs will be implemented. |

2.3	Proposals for Locality Commissioning Hubs

Proposals for Locality Commissioning Hubs are in the early stages of development and more detailed work is planned from January 2016.

It is proposed that there will be Locality Commissioning Hubs in each of the six localities in Derbyshire.

Representatives will include:

- School clusters

- Heads of Service Locality – Derbyshire Children’s Services

- Public Health

- Commissioning Manager

- Other partners based on locality/community needs

The Locality Commissioning Hubs will have the responsibility for commissioning and re-designing Early Help Services locally.  In order to do this, the Hubs will be supported with information on the commissioning process, including:

- Needs Assessment

- Budgets and arrangements for pooling budgets

- Financial monitoring

- Performance data

- Governance and reporting responsibilities

For schools that re-pool there is a great opportunity to redesign Early Help services and improve outcomes for children.  The opportunities include:

- Co-location

- Improved school readiness

- Improved attendance

- Improved transition arrangements

and full development of a Team Around the School model which will improve attainment and Ofsted judgements.

3.	Implications for Schools and Children’s Services of not Jointly

Investing

A county-wide children’s Early Help Service will no longer be sustainable.  Only schools which re-pool will have access to an Early Help Service leading to fragmentation and the possibility of concerns regarding children being missed or not responded to when concerns/needs first emerge.

Schools which don’t re-pool will only have access to Starting Point and specialist safeguarding services.  This may lead to significant delays in service delivery for children with emerging needs as specialist safeguarding services have to prioritise their statutory responsibilities for Children in Need, Child Protection and Children in Care.

The level of communication and information sharing could be reduced between schools and children’s services as schools who don’t re-pool will not have access to a School/MAT Link Worker or a Children’s Services representative at the school based multi-agency meetings where concerns regarding children with emerging needs are discussed, information is shared, work is allocated and concerns escalated if there are safeguarding concerns.  The learning from every child death (Serious Case Review) has reinforced the importance of maintaining strong communication and information sharing to keep children safe.

Schools which don’t re-pool will not have access to a wide range of evidence- based Early Help Services to prevent the emerging needs of children escalating.  This may inevitably lead to more children requiring specialist safeguarding services as emerging needs aren’t addressed.  There may also be increased pressure on universal services, e.g. Health and the voluntary sector to respond to children’s emerging needs.  Schools not re-pooling will have to decide if they are going to provide Early Help Services on an individual school basis across a wide range of services, e.g. Children’s Centres, Family Support and Youth Services.

4.	Strategic Director’s Recommendations

- Schools Forum notes the progress of REHO and approves the implementation of the next stage of Radical Rethink of the Early Help Offer county-wide.

- Schools Forum representatives agree to discuss and promote the importance of maintaining and improving Early Help Services with the schools they represent to support the county-wide roll out of the re-think of the Early Help Offer.

IAN JOHNSON

Strategic Director for Children’s Services